## Read_Me
Planting and Monitoring Data Kit (illustrative data)
Built by Les' Aullian Achmad Argito for the CarbonEthics Operations & Science Intern application, October 2026.
Read this first | Every site, plot, count and date in this file is invented to show how the sheets work. Nothing here describes a real CarbonEthics site, partner or client.
What it is for | Keeping planting and survival data clean enough to report: one row per plot planted, one row per plot visit, automatic checks, and a status line per plot that tells the team what to do next.
How to use it | 1) Set the report date and thresholds in Settings. 2) Add plots to Planting_Log. 3) Add one Monitoring row per plot visit (yellow cells only; grey cells are formulas). 4) Read the QA_Flags column and correct flagged rows at the source. 5) Read Plot_Status and Dashboard for actions. 6) Copy grey formula rows down when you add rows.
Data rule 1 | Counts are cumulative since planting: Alive + Dead + Missing must equal seedlings planted plus seedlings replanted on earlier visits.
Data rule 2 | Replanting is recorded on the visit where it happens, after that visit's count; it enters the expected total from the next visit.
Data rule 3 | Plot_Status uses only rows that pass every check. A flagged row is corrected, never deleted, and the plot shows its last clean census until then.
Data rule 4 | Stocking = living trees / seedlings in the original design (drives the replanting trigger). Survival = living trees / all seedlings ever planted on the plot (shows what replanting cost).
QA check 1: Unknown plot | Plot ID not found in Planting_Log (typos such as B3 for B03).
QA check 2: Visit before planting | Visit date earlier than the planting date (often a mistyped year).
QA check 3: Count mismatch | Alive + Dead + Missing does not equal the expected total.
QA check 4: Alive rose without replanting | More living trees than at the previous visit plus anything replanted since.
QA check 5: Duplicate visit | Same plot and date entered twice.
QA check 6: Height out of range | Mean height outside the plausible range in Settings (a slipped decimal point).
QA check 7: No observer | Nobody named as responsible for the count.
QA check 8: Loss without cause | Dead or missing seedlings recorded with no main cause.
Dropdowns | Lists in Settings stop most typos at entry; the checks catch what arrives by import, copy-paste or photos of paper sheets.
Google Sheets | Uses COUNTIFS, SUMIFS, AVERAGEIFS, SUMPRODUCT and INDEX/MATCH only, which work in Google Sheets and Excel.

## Dashboard
Dashboard
Illustrative data. Figures update from Planting_Log and Monitoring; status uses clean rows only.
Report date | 2026-09-30
Seedlings planted (design) |  | Replanted to date | Alive at last clean visit | Stocking vs design
5900 |  | 272 | 4638 | 78.61%
Plots to replant |  | Seedlings to order | Plots with census overdue | Flagged rows to correct
2 |  | 135 | 5 | 9

## Settings
Settings
Change these values; every formula reads them by name.
Name | Setting | Value | Sites | Species | Causes | Observers | Visit types
ReportDate | Report date | 2026-09-30 | Site A - seaward fringe | Rhizophora mucronata | Wave/scour | FS-1 (field staff) | Census
Trigger | Replant when stocking is below | 70% | Site B - pond dyke | Rhizophora apiculata | Barnacles | FS-2 (field staff) | Replanting
TriggerMonth | Apply the trigger from census month | 6 | Site C - sheltered lagoon | Avicennia marina | Sediment burial | PL-1 (partner lead) | Follow-up
WatchBand | Watch band above the trigger | 10% |  | Sonneratia alba | Crab damage | PL-2 (partner lead)
Target | Replant up to this stocking | 80% |  |  | Grazing | PL-3 (partner lead)
HMin | Plausible mean height, minimum (cm) | 10 |  |  | Debris/plastic
HMax | Plausible mean height, maximum (cm) | 250 |  |  | Human disturbance
OverdueDays | Census overdue after (days) | 100 |  |  | Unknown

## Planting_Log
Planting log
One row per plot planted. Yellow = input. Illustrative data.
Plot ID | Site | Zone | Planted on | Species | Seedling source | Seedlings planted | Spacing (m) | Partner group | GPS waypoint ID | Photo point ID | Notes
A01 | Site A - seaward fringe | Open fringe | 2025-10-18 | Rhizophora mucronata | Partner nursery | 500 | 1 | Partner group 1 | WP-A01 | PP-A01
A02 | Site A - seaward fringe | Open fringe | 2025-10-18 | Rhizophora mucronata | Partner nursery | 500 | 1 | Partner group 1 | WP-A02 | PP-A02
A03 | Site A - seaward fringe | Behind wave breaker | 2025-10-18 | Rhizophora mucronata | Partner nursery | 500 | 1 | Partner group 1 | WP-A03 | PP-A03
A04 | Site A - seaward fringe | Behind wave breaker | 2025-10-19 | Rhizophora mucronata | Partner nursery | 450 | 1 | Partner group 1 | WP-A04 | PP-A04
B01 | Site B - pond dyke | Dyke crest | 2026-01-24 | Rhizophora mucronata | Partner nursery | 600 | 1 | Partner group 2 | WP-B01 | PP-B01
B02 | Site B - pond dyke | Dyke crest | 2026-01-24 | Rhizophora mucronata | Partner nursery | 600 | 1 | Partner group 2 | WP-B02 | PP-B02
B03 | Site B - pond dyke | Pond floor | 2026-01-24 | Rhizophora mucronata | Partner nursery | 550 | 1 | Partner group 2 | WP-B03 | PP-B03
B04 | Site B - pond dyke | Pond floor | 2026-01-24 | Rhizophora mucronata | Partner nursery | 600 | 1 | Partner group 2 | WP-B04 | PP-B04
C01 | Site C - sheltered lagoon | Lagoon edge | 2026-03-14 | Avicennia marina | Wild propagules, partner nursery | 400 | 1.5 | Partner group 3 | WP-C01 | PP-C01
C02 | Site C - sheltered lagoon | Lagoon edge | 2026-03-14 | Avicennia marina | Wild propagules, partner nursery | 400 | 1.5 | Partner group 3 | WP-C02 | PP-C02
C03 | Site C - sheltered lagoon | Inner flat | 2026-03-14 | Avicennia marina | Wild propagules, partner nursery | 400 | 1.5 | Partner group 3 | WP-C03 | PP-C03
C04 | Site C - sheltered lagoon | Inner flat | 2026-03-14 | Avicennia marina | Wild propagules, partner nursery | 400 | 1.5 | Partner group 3 | WP-C04 | PP-C04

## Monitoring
Monitoring census
One row per plot visit. Yellow = input, grey = formula. Illustrative data with eight deliberate entry errors for the checks to catch.
Visit ID | Plot ID | Visit date | Visit type | Observer | Alive | Dead | Missing | Main cause of loss | Mean height (cm) | Replanted this visit | Notes | Site | Planted on | Months since planting | Census month | Seedlings planted | Replanted before this visit | Expected total | Survival (all planted) | Stocking (vs design) | Previous visit | Alive at previous visit | Replanted since previous | QA flags | QA issues
V001 | A01 | 2025-11-18 | Census | FS-1 (field staff) | 455 | 30 | 15 | Wave/scour | 48 | 0 |  | Site A - seaward fringe | 2025-10-18 | 1 | 1 | 500 | 0 | 500 | 91% | 91% |  |  | 0 |  | 0
V002 | A01 | 2026-01-17 | Census | FS-1 (field staff) | 360 | 90 | 50 | Wave/scour | 55 | 0 |  | Site A - seaward fringe | 2025-10-18 | 3 | 3 | 500 | 0 | 500 | 72% | 72% | 2025-11-18 | 455 | 0 |  | 0
V003 | A01 | 2026-04-18 | Census | FS-1 (field staff) | 290 | 130 | 80 | Wave/scour | 64 | 0 | Scour on the seaward edge | Site A - seaward fringe | 2025-10-18 | 6 | 6 | 500 | 0 | 500 | 58% | 58% | 2026-01-17 | 360 | 0 |  | 0
V004 | A01 | 2026-05-16 | Replanting | PL-1 (partner lead) | 286 | 132 | 82 | Wave/scour | 66 | 115 | Replanted with stakes | Site A - seaward fringe | 2025-10-18 | 6.9 | 6 | 500 | 0 | 500 | 57.2% | 57.2% | 2026-04-18 | 290 | 0 |  | 0
V005 | A02 | 2025-11-18 | Census | FS-1 (field staff) | 440 | 40 | 20 | Wave/scour | 47 | 0 |  | Site A - seaward fringe | 2025-10-18 | 1 | 1 | 500 | 0 | 500 | 88% | 88% |  |  | 0 |  | 0
V006 | A02 | 2026-01-17 | Census | FS-1 (field staff) | 330 | 110 | 60 | Barnacles | 54 | 0 |  | Site A - seaward fringe | 2025-10-18 | 3 | 3 | 500 | 0 | 500 | 66% | 66% | 2025-11-18 | 440 | 0 |  | 0
V007 | A02 | 2026-04-18 | Census | FS-1 (field staff) | 245 | 150 | 105 | Barnacles | 62 | 0 | Heavy barnacle load | Site A - seaward fringe | 2025-10-18 | 6 | 6 | 500 | 0 | 500 | 49% | 49% | 2026-01-17 | 330 | 0 |  | 0
V008 | A02 | 2026-05-16 | Replanting | PL-1 (partner lead) | 243 | 152 | 105 | Barnacles | 63 | 157 | Stems cleaned before replanting | Site A - seaward fringe | 2025-10-18 | 6.9 | 6 | 500 | 0 | 500 | 48.6% | 48.6% | 2026-04-18 | 245 | 0 |  | 0
V009 | A02 | 2026-07-18 | Follow-up | FS-2 (field staff) | 372 | 170 | 115 | Barnacles | 70 | 0 | Replanted seedlings mostly alive | Site A - seaward fringe | 2025-10-18 | 9 | 9 | 500 | 157 | 657 | 56.62% | 74.4% | 2026-05-16 | 243 | 157 |  | 0
V010 | A03 | 2025-11-18 | Census | FS-2 (field staff) | 470 | 20 | 10 | Sediment burial | 49 | 0 |  | Site A - seaward fringe | 2025-10-18 | 1 | 1 | 500 | 0 | 500 | 94% | 94% |  |  | 0 |  | 0
V011 | A03 | 2026-01-17 | Census | FS-2 (field staff) | 410 | 60 | 50 | Sediment burial | 56 | 0 | Tally sheet re-added on the boat | Site A - seaward fringe | 2025-10-18 | 3 | 3 | 500 | 0 | 500 | 82% | 82% | 2025-11-18 | 470 | 0 | Count mismatch | 1
V012 | A03 | 2026-04-18 | Census | FS-2 (field staff) | 365 | 95 | 40 | Barnacles | 66 | 0 |  | Site A - seaward fringe | 2025-10-18 | 6 | 6 | 500 | 0 | 500 | 73% | 73% | 2026-01-17 | 410 | 0 |  | 0
V013 | A04 | 2025-11-19 | Census | FS-2 (field staff) | 425 | 15 | 10 | Wave/scour | 48 | 0 |  | Site A - seaward fringe | 2025-10-19 | 1 | 1 | 450 | 0 | 450 | 94.44% | 94.44% |  |  | 0 |  | 0
V014 | A04 | 2026-01-17 | Census | FS-2 (field staff) | 380 | 45 | 25 | Wave/scour | 55 | 0 |  | Site A - seaward fringe | 2025-10-19 | 3 | 3 | 450 | 0 | 450 | 84.44% | 84.44% | 2025-11-19 | 425 | 0 |  | 0
V015 | A04 | 2026-04-18 | Census | FS-2 (field staff) | 300 | 95 | 55 | Barnacles | 65 | 0 |  | Site A - seaward fringe | 2025-10-19 | 5.9 | 6 | 450 | 0 | 450 | 66.67% | 66.67% | 2026-01-17 | 380 | 0 |  | 0
V016 | B01 | 2026-02-24 | Census | PL-2 (partner lead) | 575 | 15 | 10 |  | 46 | 0 |  | Site B - pond dyke | 2026-01-24 | 1 | 1 | 600 | 0 | 600 | 95.83% | 95.83% |  |  | 0 | Loss without cause | 1
V017 | B01 | 2026-04-25 | Census | PL-2 (partner lead) | 540 | 35 | 25 | Crab damage | 52 | 0 |  | Site B - pond dyke | 2026-01-24 | 3 | 3 | 600 | 0 | 600 | 90% | 90% | 2026-02-24 | 575 | 0 |  | 0
V018 | B01 | 2026-07-25 | Census | FS-1 (field staff) | 510 | 55 | 35 | Crab damage | 63 | 0 |  | Site B - pond dyke | 2026-01-24 | 6 | 6 | 600 | 0 | 600 | 85% | 85% | 2026-04-25 | 540 | 0 |  | 0
V019 | B02 | 2026-02-24 | Census | PL-2 (partner lead) | 580 | 12 | 8 | Crab damage | 47 | 0 |  | Site B - pond dyke | 2026-01-24 | 1 | 1 | 600 | 0 | 600 | 96.67% | 96.67% |  |  | 0 |  | 0
V020 | B02 | 2026-04-25 | Census | PL-2 (partner lead) | 545 | 35 | 20 | Crab damage | 53 | 0 |  | Site B - pond dyke | 2026-01-24 | 3 | 3 | 600 | 0 | 600 | 90.83% | 90.83% | 2026-02-24 | 580 | 0 |  | 0
V021 | B02 | 2026-07-25 | Census | FS-1 (field staff) | 562 | 23 | 15 | Crab damage | 62 | 0 |  | Site B - pond dyke | 2026-01-24 | 6 | 6 | 600 | 0 | 600 | 93.67% | 93.67% | 2026-04-25 | 545 | 0 | Alive rose without replanting | 1
V022 | B03 | 2026-02-24 | Census | PL-2 (partner lead) | 520 | 20 | 10 | Sediment burial | 45 | 0 |  | Site B - pond dyke | 2026-01-24 | 1 | 1 | 550 | 0 | 550 | 94.55% | 94.55% |  |  | 0 |  | 0
V023 | B3 | 2026-04-25 | Census | PL-2 (partner lead) | 455 | 60 | 35 | Sediment burial | 51 | 0 | [6 empty] | 0 | [5 empty] | 0 | Unknown plot | 1
V024 | B03 | 2026-07-25 | Census | FS-1 (field staff) | 365 | 115 | 70 | Sediment burial | 58 | 0 | Silt over the lower rows | Site B - pond dyke | 2026-01-24 | 6 | 6 | 550 | 0 | 550 | 66.36% | 66.36% | 2026-02-24 | 520 | 0 |  | 0
V025 | B04 | 2026-02-24 | Census | PL-2 (partner lead) | 585 | 10 | 5 | Crab damage | 46 | 0 |  | Site B - pond dyke | 2026-01-24 | 1 | 1 | 600 | 0 | 600 | 97.5% | 97.5% |  |  | 0 |  | 0
V026 | B04 | 2026-04-25 | Census | PL-2 (partner lead) | 560 | 25 | 15 | Crab damage | 850 | 0 |  | Site B - pond dyke | 2026-01-24 | 3 | 3 | 600 | 0 | 600 | 93.33% | 93.33% | 2026-02-24 | 585 | 0 | Height out of range | 1
V027 | B04 | 2026-07-25 | Census | FS-1 (field staff) | 535 | 40 | 25 | Crab damage | 63 | 0 |  | Site B - pond dyke | 2026-01-24 | 6 | 6 | 600 | 0 | 600 | 89.17% | 89.17% | 2026-04-25 | 560 | 0 |  | 0
V028 | C01 | 2025-04-14 | Census | PL-3 (partner lead) | 388 | 8 | 4 | Debris/plastic | 30 | 0 |  | Site C - sheltered lagoon | 2026-03-14 | -11 | 1 | 400 | 0 | 400 | 97% | 97% |  |  | 0 | Visit before planting | 1
V029 | C01 | 2026-06-13 | Census | PL-3 (partner lead) | 365 | 22 | 13 | Debris/plastic | 38 | 0 |  | Site C - sheltered lagoon | 2026-03-14 | 3 | 3 | 400 | 0 | 400 | 91.25% | 91.25% | 2025-04-14 | 388 | 0 |  | 0
V030 | C01 | 2026-09-12 | Census | FS-2 (field staff) | 340 | 38 | 22 | Debris/plastic | 50 | 0 | Plastic caught on seedlings | Site C - sheltered lagoon | 2026-03-14 | 6 | 6 | 400 | 0 | 400 | 85% | 85% | 2026-06-13 | 365 | 0 |  | 0
V031 | C02 | 2026-04-14 | Census | PL-3 (partner lead) | 380 | 12 | 8 | Grazing | 31 | 0 | Goats seen near the edge | Site C - sheltered lagoon | 2026-03-14 | 1 | 1 | 400 | 0 | 400 | 95% | 95% |  |  | 0 |  | 0
V032 | C02 | 2026-06-13 | Census | PL-3 (partner lead) | 330 | 45 | 25 | Grazing | 37 | 0 |  | Site C - sheltered lagoon | 2026-03-14 | 3 | 3 | 400 | 0 | 400 | 82.5% | 82.5% | 2026-04-14 | 380 | 0 |  | 0
V033 | C02 | 2026-09-12 | Census | FS-2 (field staff) | 290 | 70 | 40 | Grazing | 49 | 0 |  | Site C - sheltered lagoon | 2026-03-14 | 6 | 6 | 400 | 0 | 400 | 72.5% | 72.5% | 2026-06-13 | 330 | 0 |  | 0
V034 | C03 | 2026-04-14 | Census | PL-3 (partner lead) | 392 | 5 | 3 | Debris/plastic | 32 | 0 |  | Site C - sheltered lagoon | 2026-03-14 | 1 | 1 | 400 | 0 | 400 | 98% | 98% |  |  | 0 |  | 0
V035 | C03 | 2026-06-13 | Census | PL-3 (partner lead) | 372 | 18 | 10 | Debris/plastic | 39 | 0 |  | Site C - sheltered lagoon | 2026-03-14 | 3 | 3 | 400 | 0 | 400 | 93% | 93% | 2026-04-14 | 392 | 0 | Duplicate visit | 1
V036 | C03 | 2026-06-13 | Census | PL-3 (partner lead) | 372 | 18 | 10 | Debris/plastic | 39 | 0 | Entered from photo of the sheet | Site C - sheltered lagoon | 2026-03-14 | 3 | 3 | 400 | 0 | 400 | 93% | 93% | 2026-04-14 | 392 | 0 | Duplicate visit | 1
V037 | C03 | 2026-09-12 | Census | FS-2 (field staff) | 355 | 30 | 15 | Debris/plastic | 51 | 0 |  | Site C - sheltered lagoon | 2026-03-14 | 6 | 6 | 400 | 0 | 400 | 88.75% | 88.75% | 2026-06-13 | 744 | 0 |  | 0
V038 | C04 | 2026-04-14 | Census | PL-3 (partner lead) | 390 | 6 | 4 | Crab damage | 31 | 0 |  | Site C - sheltered lagoon | 2026-03-14 | 1 | 1 | 400 | 0 | 400 | 97.5% | 97.5% |  |  | 0 |  | 0
V039 | C04 | 2026-06-13 | Census | PL-3 (partner lead) | 375 | 15 | 10 | Crab damage | 38 | 0 |  | Site C - sheltered lagoon | 2026-03-14 | 3 | 3 | 400 | 0 | 400 | 93.75% | 93.75% | 2026-04-14 | 390 | 0 |  | 0
V040 | C04 | 2026-09-12 | Census |  | 362 | 25 | 13 | Crab damage | 50 | 0 |  | Site C - sheltered lagoon | 2026-03-14 | 6 | 6 | 400 | 0 | 400 | 90.5% | 90.5% | 2026-06-13 | 375 | 0 | No observer | 1
Formulas:
Planted on = IF([Plot ID]="","",IFERROR(INDEX(Planting_Log!$D5:D60,MATCH([Plot ID],Planting_Log!$A5:A60,0)),""))
Previous visit = IF([Plot ID]="","",IF(COUNTIFS(B5:B200,[Plot ID],C5:C200,"<"&[Visit date])=0,"",SUMPRODUCT(MAX((B5:B200=[Plot ID])*(C5:C200<[Visit date])*C5:C200))))

## Plot_Status
Plot status
One row per plot, from the last census that passed every check. Read Next action first.
Plot ID | Site | Seedlings planted | Planted on | Last clean visit | Census month at last visit | Alive at last visit | Replanted before last visit | Stocking (vs design) | Survival (all planted) | Replanted at last visit | Status | Seedlings to replant | Days since last visit | Open QA rows | Next action | Seedlings lost | Main cause at last visit | Trigger
A01 | Site A - seaward fringe | 500 | 2025-10-18 | 2026-05-16 | 6 | 286 | 0 | 57.2% | 57.2% | 115 | Replanted, recheck | 0 | 137 | 0 | Census overdue | 214 | Wave/scour | 70%
A02 | Site A - seaward fringe | 500 | 2025-10-18 | 2026-07-18 | 9 | 372 | 157 | 74.4% | 56.62% | 0 | Watch | 0 | 74 | 0 | Check the cause at the next visit | 285 | Barnacles | 70%
A03 | Site A - seaward fringe | 500 | 2025-10-18 | 2026-04-18 | 6 | 365 | 0 | 73% | 73% | 0 | Watch | 0 | 165 | 1 | Census overdue; fix 1 flagged row | 135 | Barnacles | 70%
A04 | Site A - seaward fringe | 450 | 2025-10-19 | 2026-04-18 | 6 | 300 | 0 | 66.67% | 66.67% | 0 | Replant | 60 | 165 | 0 | Replant 60 seedlings with the partner group; census overdue | 150 | Barnacles | 70%
B01 | Site B - pond dyke | 600 | 2026-01-24 | 2026-07-25 | 6 | 510 | 0 | 85% | 85% | 0 | On track | 0 | 67 | 1 | Routine census; fix 1 flagged row | 90 | Crab damage | 70%
B02 | Site B - pond dyke | 600 | 2026-01-24 | 2026-04-25 | 3 | 545 | 0 | 90.83% | 90.83% | 0 | On track | 0 | 158 | 1 | Census overdue; fix 1 flagged row | 55 | Crab damage | 70%
B03 | Site B - pond dyke | 550 | 2026-01-24 | 2026-07-25 | 6 | 365 | 0 | 66.36% | 66.36% | 0 | Replant | 75 | 67 | 0 | Replant 75 seedlings with the partner group | 185 | Sediment burial | 70%
B04 | Site B - pond dyke | 600 | 2026-01-24 | 2026-07-25 | 6 | 535 | 0 | 89.17% | 89.17% | 0 | On track | 0 | 67 | 1 | Routine census; fix 1 flagged row | 65 | Crab damage | 70%
C01 | Site C - sheltered lagoon | 400 | 2026-03-14 | 2026-09-12 | 6 | 340 | 0 | 85% | 85% | 0 | On track | 0 | 18 | 1 | Routine census; fix 1 flagged row | 60 | Debris/plastic | 70%
C02 | Site C - sheltered lagoon | 400 | 2026-03-14 | 2026-09-12 | 6 | 290 | 0 | 72.5% | 72.5% | 0 | Watch | 0 | 18 | 0 | Check the cause at the next visit | 110 | Grazing | 70%
C03 | Site C - sheltered lagoon | 400 | 2026-03-14 | 2026-09-12 | 6 | 355 | 0 | 88.75% | 88.75% | 0 | On track | 0 | 18 | 2 | Routine census; fix 2 flagged rows | 45 | Debris/plastic | 70%
C04 | Site C - sheltered lagoon | 400 | 2026-03-14 | 2026-06-13 | 3 | 375 | 0 | 93.75% | 93.75% | 0 | On track | 0 | 109 | 1 | Census overdue; fix 1 flagged row | 25 | Crab damage | 70%
Formulas:
Planted on = IF([Plot ID]="","",Planting_Log!D5)
Last clean visit = IF([Plot ID]="","",IF(SUMPRODUCT((Monitoring!$B5:B200=[Plot ID])*(Monitoring!$Z5:Z200=0)*(Monitoring!$C5:C200<>""))=0,"",SUMPRODUCT(MAX((Monitoring!$B5:B200=[Plot ID])*(Monitoring!$Z5:Z200=0)*Monitoring!$C5:C200))))

## Site_Summary
Site summary
Totals per site, stocking by census month, and losses by main cause.
Site | Plots | Seedlings planted | Replanted to date | Alive at last clean visit | Stocking (vs design) | Plots to replant | Seedlings to order | Plots with census overdue | Flagged rows open
Site A - seaward fringe | 4 | 1950 | 272 | 1323 | 67.85% | 1 | 60 | 3 | 1
Site B - pond dyke | 4 | 2350 | 0 | 1955 | 83.19% | 1 | 75 | 1 | 3
Site C - sheltered lagoon | 4 | 1600 | 0 | 1360 | 85% | 0 | 0 | 1 | 4
All sites | 12 | 5900 | 272 | 4638 | 78.61% | 2 | 135 | 5 | 8
Rows with an unknown plot ID | [8 empty] | 1
Stocking by census month (clean census rows only) |  |  |  |  | Seedlings lost by main cause (cause recorded at each plot's last clean visit)
Site | Month 1 | Month 3 | Month 6 |  | Main cause | Plots | Seedlings lost
Site A - seaward fringe | 91.86% | 74.15% | 61.67% |  | Wave/scour | 1 | 214
Site B - pond dyke | 96.24% | 90.42% | 80.18% |  | Barnacles | 3 | 570
Site C - sheltered lagoon | 96.83% | 89.17% | 82.08% |  | Sediment burial | 1 | 185
[5 empty] | Crab damage | 4 | 235
[5 empty] | Grazing | 1 | 110
[5 empty] | Debris/plastic | 2 | 105
[5 empty] | Human disturbance | 0 | 0
[5 empty] | Unknown | 0 | 0

## Field_Day_SOP
Planting day: standard operating procedure (draft)
A draft built from public restoration guidance and my own field work; to be adapted to CarbonEthics' own SOPs.
No. | Phase | Step | What good looks like | Owner | Record kept
1 | T-14 to T-7: plan | Confirm the plots to be planted, their boundaries and waypoint IDs | Every plot has an ID in Planting_Log before the day | Ops intern | Planting_Log rows
2 | T-14 to T-7: plan | Choose the date and start time from the tide table | Planting on a falling-to-low tide; crew off the flat before the flood returns | Field lead | Tide window in the day plan
3 | T-14 to T-7: plan | Check that each zone is plantable | Elevation and flooding compared with nearby natural mangroves; species matched to the zone | Science team | Site note with photos
4 | T-14 to T-7: plan | Agree roles, numbers and compensation with the partner group in writing | Who plants, who maintains, how much and when, in Bahasa Indonesia | Ops lead + partner lead | Signed agreement or written confirmation on file
5 | T-14 to T-7: plan | Order seedlings by zone | Planned count plus 10% spare; minimum height and leaf count stated in the order | Ops intern | Seedling order
6 | T-14 to T-7: plan | Permits and notifications | Village office or area authority informed as required; client briefing pack for corporate plantings | Ops lead | Letter or message on file
7 | T-14 to T-7: plan | Participant list and safety kit | Emergency contacts; boots, gloves, first aid, water; life jackets for any boat transfer | Ops intern | Participant list, kit checklist
8 | T-1: check | Seedling quality check at the nursery | Count, height, healthy leaves, intact root ball, no pests; reject below standard | Science team + partner | QC sheet: accepted and rejected
9 | T-1: check | Weather and sea check | Marine forecast checked; go or no-go sent by 06:00 on the day; backup date agreed | Field lead | Go/no-go message
10 | T-1: check | Prepare data tools | Forms loaded, plot tags with batch codes printed, GPS and phones charged | Ops intern | Ready checklist
11 | Day: plant | Safety and method briefing | Tide time, mud safety, planting depth, staking and tying, nothing plastic left behind | Field lead | Briefing done before planting starts
12 | Day: plant | Assign plots to teams, one recorder per plot | Each recorder tallies seedlings planted in their plot | Ops intern | Tally per plot
13 | Day: plant | Take photo-point pictures | Same position and direction on every visit, plot ID in the file name | Ops intern | Photo log
14 | Day: plant | Collect polybags and ties | Bags out equals bags back | Everyone | Bag count
15 | Close-out (same day) | Three-way seedling count | Delivered = planted + spare returned + rejected; signed by field lead and partner lead | Ops intern | Signed tally
16 | Close-out (same day) | Enter the data and run the checks | Rows entered the same day, paper sheets photographed, QA flags at zero | Ops intern | Planting_Log and Monitoring rows
17 | Follow-up | Census at months 1, 3, 6 and 12 | Replanting by the agreed terms when stocking falls below the trigger | Science team + partner | Monitoring rows, Plot_Status actions
18 | Follow-up | Pay the partner group on the agreed date and share results back | Payment logged; results explained to the group in a short session | Ops lead + finance | Payment log, session note

## Risk_Register
Risk register for planting and monitoring (draft)
Likelihood and severity 1 (low) to 3 (high). Score = likelihood x severity; 6 or 9 = High, 3 or 4 = Medium, 1 or 2 = Low.
ID | Risk | Cause or trigger | Likelihood | Severity | Score | Rating | Control before the day | Control on the day | Owner | Early warning
R01 | Seedlings planted in the wrong zone (too low, flooded too long) | Site chosen by convenience, not by flooding | 2 | 3 | 6 | High | Compare elevation and flooding with nearby natural mangroves; pilot plot before scaling | Plant only inside the marked zone | Science team | Month-1 losses above 20% in the lowest plots
R02 | Tide window missed | Ceremony or boat delay | 2 | 3 | 6 | High | Schedule from the tide table; ceremony after planting or kept short | Hard stop time announced at the briefing | Field lead | Start delayed by more than 30 minutes
R03 | Wave exposure and scour on open fringe | Exposed plots, no shelter | 2 | 3 | 6 | High | Plant sheltered zones first, behind wave breakers where they exist; stake seedlings | Check stakes and ties before leaving | Science team | Missing counts rising at month 1
R04 | Barnacle load and debris on stems | Low maintenance between visits | 2 | 2 | 4 | Medium | Monthly cleaning duty written into the partner agreement | Show cleaning method at the briefing | Partner lead | Barnacles named as main cause at a census
R05 | Poor seedling quality | Too young, damaged or diseased stock | 2 | 2 | 4 | Medium | Nursery check on T-1 with written reject criteria; 10% spare | Recorder sets aside rejected seedlings | Science team | Rejection rate above 10%
R06 | Counts do not reconcile (delivered, planted, reported) | Tally errors, late data entry | 2 | 3 | 6 | High | One recorder per plot; tally sheets printed | Three-way count signed; same-day entry with QA checks | Ops intern | QA flags on entry
R07 | Plot cannot be found again | No marker, GPS drift, photo point not fixed | 2 | 2 | 4 | Medium | Fixed markers, waypoint ID and photo point for every plot | Photo of each marker | Ops intern | Census note: plot not located
R08 | Partner group unclear on roles or payment | Terms agreed verbally only | 2 | 3 | 6 | High | Written agreement in Bahasa Indonesia; named contact; payment date | Repeat the terms at the briefing | Ops lead | Maintenance visits missed
R09 | Grazing, trampling or human disturbance | Livestock or foot traffic near the site | 1 | 2 | 2 | Low | Agree signs or simple fencing with the village where livestock roam | Mark planted rows clearly | Partner lead | Grazing named as main cause
R10 | Injury: cuts, slips, heat, boat transfer | Mud, shells, sun, small boats | 1 | 3 | 3 | Medium | PPE list, first-aid kit, life jackets, buddy system | Safety briefing; water breaks | Field lead | Any near-miss reported
R11 | Bad weather or high waves | Season, storms | 2 | 2 | 4 | Medium | Marine forecast check; go or no-go by 06:00; backup date | Stop work if waves or lightning | Field lead | Forecast warning issued
R12 | Plastic left on site | Polybags and ties dropped | 2 | 1 | 2 | Low | Bag count planned | Bags out equals bags back | Everyone | Bag count short